## Releases
Release	Sprint	Starting Date	Ending Date	Remaining	Description
1	1	1-Nov-13	9-Nov-13	Err:502

## Pre-Game
Start Date	11/28/2011
			Working Day	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
#	Task		Remaining	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
1	Gather requirement
2	Define Architecture
3	Build Project framework

## Product Backlog
User		StoryID	Category	Story	Constraint	BR	Sprint	Priority	Estimated	Actual	Remaining		SD			0.20
Trainee				As a trainee
		T1	Course	View instructions about what the things I have to learn			1	1	4	0	1			4.8	0
		T2	Subject	View the instruction about a thing I have to learn			1	1	4	0	5			4.8	0
		T3	Subject	Report day by day			1	2	15	0	13			18	0
		T4	Course	View my current progress			1	1	4	0	5			4.8	0
		T5	Calendar	View my training calendar			1	3	20	0	4			24	0
		T6	Activity	View all histories of my activity in course, in subject			1	2	7
		T7	User	Can signin			1	1	2
		T8	User	View my profile, member profile			1	2	4
		T9	User	Edit my profile			1	2	2
		T10	User	View members of course			1	1	1
		T11	Activity	View all activity histories of course			1	2	4
		T12	Course	Can start course			1	2	7
														0	0
Suppervisor				As a suppervisor										0	0
		S1		Can signin, signout			1	1	0	0	0			0	0
		S2		View my profile, other suppervisor profile and trainee profile			1	1	0	0	0			0	0
		S3		Can edit my profile
		S4		View all courses
		S5		View course detail
		S6		Can add suppervisors to course
		S7		Can make a new course
		S8		Can edit a new course (and customize structure of course)
		S9		Can delete a course
		S10		View subject detail of course
		S11		View all trainees in a course
		S12		Can assign trainees to course
		S13		View course progress of trainee
		S14		Can decide finish/un-finish the Course of a trainee
		S15		Can decide finish/un-finish the Subject of a trainee
		S16		Can forced finish a course
		S17		View all subject
		S18		View subject detail (with structure)
		S19		Can create new subject (with structure)
		S20		Can edit a subject (with structure)
		S21		Can delete a subject
		S22		View all trainees
		S23		Can add new a trainee
		S24		Can edit a trainee
		S25		Can delete trainees

														0	0
Operator				As CG's Operator										0	0
		O1					1	1	0	0	0			0	0
		O2					1	1	0	0	0			0	0
		O3					1	1	0	0	0			0	0
														0	0

## Business Rules
ID	Description	Related Rules	References	Note
BR1
BR2
BR3
BR4
BR5
BR6
BR7
BR8
BR9
BR10
BR11
BR15

	Constraint
	Computation
	Action/Switch action/Execute action	Enable/Disable/Execute a process
	Data Action	A data action rule creates, modifies or deletes data
	Presentation Action

	ID
	Description	Example	Workflow	Workflow
	Related Rules
	References
	Assumptions
	Notes	Concerns

## Sprint1
				Lost Hour	0					Holiday
				WH	42
				Tuan	0
				Ninh	7
				Lan	7
				Ky	7
				Mui	7
				Quynh	7
				Giang	7
				Start Date	11/1/2013
				Date	01	02	03	04	05	06	07	08	09
				W	R	1	1	1	2	3	4	5	6	6	Saturday
				54%	46%	222	222	222	180	138	96	54	12	12	Sunday
StoryID	TaskID	Task					119	103	222	222	222	207	164	131	103	103	103
T0	001	Make sprint backlog					0	21	21	21	6	0	0	0	0	0
T0	002	Design database model					Mui	0	4	4	4	4	0	0	0	0	0
T0	003	Review DB					1	2	2	2	2	1	1	1	1	1
T1	101	Design General information page					Lan	0	1	1	1	1	0	0	0	0	0
T2	201	Design Subject instruction page					Ky	0	1	1	1	1	0	0	0	0	0
T2	202	Update Design Subject instruction page					Ninh	0	1	1	1	1	0	0	0	0	0
T2	203	Design Task list page					Quynh	0	1	1	1	1	0	0	0	0	0
T2	204	Design Task detail page					Quynh	0	1	1	1	1	0	0	0	0	0
T7	701	Design Signin page					Ninh	0	1	1	1	1	0	0	0	0	0
T8	801	Design User profile page					Ninh	0	1	1	1	1	0	0	0	0	0
T9	901	Design User profile edit page					Ninh	0	1	1	1	1	0	0	0	0	0
T6	601	Design Activities log page					Lan	0	1	1	1	1	0	0	0	0	0
T11	1101	Design Activities log page (for all user)					Lan	0	1	1	1	1	0	0	0	0	0
T10	1001	Design User list page					Ninh	0	1	1	1	1	0	0	0	0	0
T0	004	Design Home page					Lan	0	3	3	3	3	0	0	0	0	0
T0	005	Review Design pages					Tuan	0	2	2	2	2	0	0	0	0	0
T0	006	Make framework					Giang	0	2	2	2	2	0	0	0	0	0
T0	007	Implement database model					Ky	0	2	2	2	2	0	0	0	0	0
T0	008	Writing sample data for tests					Mui	0	2	2	2	2	0	0	0	0	0
T0	010	Create static home pages					Giang	0	4	4	4	4	0	0	0	0	0
T7	702	Make signin page					Giang	0	4	4	4	4	0	0	0	0	0
T3	301	Create report view page					Lan	3	6	6	6	6	6	6	3	3	3
T3	302	Create report update function					Mui	7	10	10	10	10	10	10	7	7	7
T10	1002	List all trainees					Quynh	0	2	2	2	2	0	0	0	0	0
T8	802	Create public profile page of trainee					Mui	0	6	6	6	6	6	0	0	0	0
T4	401	Create progress bar on trainee home page					Ninh	4	7	7	7	7	7	7	4	4	4
T2	205	Create progress bar on subject page					Lan	3	7	7	7	7	7	7	3	3	3
T6	602	Create trainee activity feed in trainee home page					Quynh	2	4	4	4	4	4	4	2	2	2
T6	603	Create trainee activity feed of a subject on subject page					Quynh	5	10	10	10	10	10	10	5	5	5
T5	501	Create Calendar page					0	0	0	0	0	0	0	0	0	0
T12	1201	Make start course function					Giang	0	10	10	10	10	10	0	0	0	0
T2	208	Make finish subject function					Giang	0	7	7	7	7	7	7	0	0	0
T1	102	Create course view page					Ky	0	7	7	7	7	7	0	0	0	0
T9	902	Create edit profile page					Mui	0	2	2	2	2	2	0	0	0	0
T0	011	Make home page, layout & css					Ninh	0	7	7	7	7	7	0	0	0	0
T0	014	Apply css					Ninh	4	6	6	6	6	6	5	4	4	4
T11	1102	Create trainee activity feed of all training in course					7	7	7	7	7	7	7	7	7	7
T7	703	Test signin page					Ky	1	1	1	1	1	1	1	1	1	1
T8	803	Test profile page					Giang	1	1	1	1	1	1	1	1	1	1
T9	903	Test edit profie					Giang	1	1	1	1	1	1	1	1	1	1
T1	103	Test Course instruction page					1	1	1	1	1	1	1	1	1	1
T4	402	Test Course progress bar					1	1	1	1	1	1	1	1	1	1
T2	206	Test Subject instruction page					1	1	1	1	1	1	1	1	1	1
T2	207	Test Subject progress bar					1	1	1	1	1	1	1	1	1	1
T12	1202	Test Start course function					3	3	3	3	3	3	3	3	3	3
T11	1103	Test Activity of course					2	2	2	2	2	2	2	2	2	2
T6	604	Test my Activity in course					Giang	2	2	2	2	2	2	2	2	2	2
T6	605	Test my Activity in subject					1	1	1	1	1	1	1	1	1	1
T3	303	Test update report function					3	3	3	3	3	3	3	3	3	3
T10	1003	Test user list					1	1	1	1	1	1	1	1	1	1
T5	502	Test calendar					4	4	4	4	4	4	4	4	4	4
T0	012	Test home page					2	2	2	2	2	2	2	2	2	2
T0	013	Fix bug for all					42	42	42	42	42	42	42	42	42	42

ISSUES:
	TuanCA
	NinhTMH
	LanDT
	Ky
	Mui
	Quynh
	Giang

## ScrumIntro
Roles
	Product owner
		• defines product, releases, ROI, ...					• respects team estimates
		• represents customer and users for the team					• respects sprint planning
		• manages the Product Backlog
		• accepts work

	Team
		• typically 5-9 people					• respects Product Owner prio’s
		• cross-functional					• respects Scrum values and process
		• self-organizing and empowered

	Master
		• guards the Scrum process and the improvement cycle					• respects team decisions
		• removes impediments
		• motivates and coaches the team
		• facilitates collaboration

Artifacts
		• Product backlog
		• Sprint backlog
		• Burndown charts

Ceremonies
		• Estimation meeting
		• Planning meeting
		• Daily Scrum
		• Sprint review
		– demo
		– retrospective

Phases
	Planning
	Architecture / High level design
	Development		iteractive cycle

References:
	http://en.wikipedia.org/wiki/Scrum_(development)#Core_Scrum_roles
	http://www.xpday.net/html/Xpday2009/ScrumForDummies_handouts.pdf
	http://agileintro.wordpress.com/2008/01/10/all-about-scrum/

## 'file:///home/chuanhtuan/rails_projects/tms/document/TMS_Backlog_v1.0.xlsx'#Product Backlog
Sprint				Remaining

1				10
1				15
1				20
1				4
1				20
1				20

1				0
1				0
1				0

1				0
1				0
1				0