## Releases
Release	Sprint	Starting Date	Ending Date	Remaining	Description
1	1	1-Nov-13	9-Nov-13	Err:502

## Pre-Game
Start Date	11/28/2011
			Working Day	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
#	Task		Remaining	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
1	Gather requirement
2	Define Architecture
3	Build Project framework

## Product Backlog
User		StoryID	Category	Story	Constraint	BR	Sprint	Priority	Estimated	Actual	Remaining		SD			0.20
Trainee				As a trainee
		T1	Course	View instructions about what the things I have to learn			1	1	4	0	1			4.8	0
		T2	Subject	View the instruction about a thing I have to learn			1	1	4	0	2			4.8	0
		T3	Subject	Report day by day			1	2	15	0	3			18	0
		T4	Course	View my current progress			1	1	4	0	1			4.8	0
		T5	Calendar	View my training calendar			1	3	20	0	4			24	0
		T6	Activity	View all histories of my activity in course, in subject			1	2	7
		T7	User	Can signin			1	1	2
		T8	User	View my profile, member profile			1	2	4
		T9	User	Edit my profile			1	2	2
		T10	User	View members of course			1	1	1
		T11	Activity	View all activity histories of course			1	2	4
		T12	Course	Can start course			1	2	7
														0	0
Suppervisor				As a suppervisor										0	0
		S1		Can signin, signout			1	1	0	0	0			0	0
		S2		View my profile, other suppervisor profile and trainee profile			1	1	0	0	0			0	0
		S3		Can edit my profile
		S4		View all courses
		S5		View course detail
		S6		Can add suppervisors to course
		S7		Can make a new course
		S8		Can edit a new course (and customize structure of course)
		S9		Can delete a course
		S10		View subject detail of course
		S11		View all trainees in a course
		S12		Can assign trainees to course
		S13		View course progress of trainee
		S14		Can decide finish/un-finish the Course of a trainee
		S15		Can decide finish/un-finish the Subject of a trainee
		S16		Can forced finish a course
		S17		View all subject
		S18		View subject detail (with structure)
		S19		Can create new subject (with structure)
		S20		Can edit a subject (with structure)
		S21		Can delete a subject
		S22		View all trainees
		S23		Can add new a trainee
		S24		Can edit a trainee
		S25		Can delete trainees

														0	0
Operator				As CG's Operator										0	0
		O1					1	1	0	0	0			0	0
		O2					1	1	0	0	0			0	0
		O3					1	1	0	0	0			0	0
														0	0

## Business Rules
ID	Description	Related Rules	References	Note
BR1
BR2
BR3
BR4
BR5
BR6
BR7
BR8
BR9
BR10
BR11
BR15

	Constraint
	Computation
	Action/Switch action/Execute action	Enable/Disable/Execute a process
	Data Action	A data action rule creates, modifies or deletes data
	Presentation Action

	ID
	Description	Example	Workflow	Workflow
	Related Rules
	References
	Assumptions
	Notes	Concerns

## Master
				Lost Hour	0					Holiday
				WH	35
				Hang	5
				Ninh	5
				Lan	5
				Ky	5
				Mui	5
				Quynh	5
				Giang	5
				Start Date	11/1/2013
				Date	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16
				W	R	1	1	1	2	3	4	5	6	6	6	7	8	9	10	11	11	11	12	13	14	15	16	16	16	17	18	19	20	21	21	21	22	23	24	25	26	26	26	27	28	29	30	31	31	31	32	Saturday
				26%	74%	729	729	729	694	659	624	589	554	554	554	519	484	449	414	379	379	379	344	309	274	239	204	204	204	169	134	99	64	29	29	29	-6	-41	-76	-111	-146	-146	-146	-181	-216	-251	-286	-321	-321	-321	-356	Sunday
StoryID	Category	Task					189	540	729	729	729	729	729	729	729	729	729	729	729	729	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540	540
	Trainee	Design frontend pages					0	60	60	60	60	60	60	60	60	60	60	60	60	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0001	Trainee	View instructions about what the things I have to learn					0	10	10	10	10	10	10	10	10	10	10	10	10	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0002	Trainee	View the instruction about a thing I have to learn					0	10	10	10	10	10	10	10	10	10	10	10	10	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0003	Trainee	Report day by day					0	15	15	15	15	15	15	15	15	15	15	15	15	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0004	Trainee	View my current progress					0	10	10	10	10	10	10	10	10	10	10	10	10	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0005	Trainee	View my training calendar					0	20	20	20	20	20	20	20	20	20	20	20	20	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0006	Trainee	View all histories of my activity in course, in subject					0	15	15	15	15	15	15	15	15	15	15	15	15	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0007	Trainee	Can signin					0	2	2	2	2	2	2	2	2	2	2	2	2	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0008	Trainee	View my profile, member profile					0	5	5	5	5	5	5	5	5	5	5	5	5	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0009	Trainee	Edit my profile					0	2	2	2	2	2	2	2	2	2	2	2	2	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0010	Trainee	View members of course					0	5	5	5	5	5	5	5	5	5	5	5	5	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0011	Trainee	View all activity histories of course					0	10	10	10	10	10	10	10	10	10	10	10	10	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
0012	Trainee	Can start course					0	15	15	15	15	15	15	15	15	15	15	15	15	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
	Trainee	Refactor code					0	70	70	70	70	70	70	70	70	70	70	70	70	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
	Trainee	Test					30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30	30
	Trainee	Fix bugs					60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60	60
	Supervisor	Design Backend pages					70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70
0013	Supervisor	Can signin, signout					3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3	3
0014	Supervisor	View my profile, other suppervisor profile and trainee profile					5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5
0015	Supervisor	Can edit my profile					2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2	2
0016	Supervisor	View all courses					5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5
0017	Supervisor	View course detail					10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10
0018	Supervisor	Can add suppervisors to course					5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5
0019	Supervisor	Can make a new course					10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10
0020	Supervisor	Can edit a new course (and customize structure of course)					10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10
0021	Supervisor	Can delete a course					5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5
0022	Supervisor	View subject detail of course					10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10
0023	Supervisor	View all trainees in a course					5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5
0024	Supervisor	Can assign trainees to course					5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5
0025	Supervisor	View course progress of trainee					5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5
0026	Supervisor	Can decide finish/un-finish the Course of a trainee					10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10
0027	Supervisor	Can decide finish/un-finish the Subject of a trainee					10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10
0028	Supervisor	Can forced finish a course					10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10
0029	Supervisor	View all subject					5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5
0030	Supervisor	View subject detail (with structure)					10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10
0031	Supervisor	Can create new subject (with structure)					10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10
0032	Supervisor	Can edit a subject (with structure)					10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10	10
0033	Supervisor	Can delete a subject					5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5
0034	Supervisor	View all trainees					5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5
0035	Supervisor	Can add new a trainee					5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5
0036	Supervisor	Can edit a trainee					5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5
0037	Supervisor	Can delete trainees					5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5	5
	Supervisor	Refactor code					70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70
	Supervisor	Test					70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70
	Supervisor	Fix bugs					70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70	70

ISSUES:
	TuanCA
	NinhTMH
	LanDT
	Ky
	Mui
	Quynh
	Giang
	Hang

## Sprint1
				Lost Hour	0					Holiday
				WH	36
				Tuan	0
				Ninh	6
				Lan	6
				Ky	6
				Mui	6
				Quynh	6
				Giang	6
				Start Date	11/1/2013
				Date	01	02	03	04	05	06	07	08	09
				W	R	1	1	1	2	3	4	5	6	6	Saturday
				81%	19%	180	180	180	144	108	72	36	0	0	Sunday
StoryID	TaskID	Task					145	35	180	180	180	165	122	89	61	35	35
T0	0001	Make sprint backlog					0	21	21	21	6	0	0	0	0	0
T0	0002	Design database model					Mui	0	4	4	4	4	0	0	0	0	0
T0	0003	Review DB					0	2	2	2	2	1	1	1	0	0
T1	0101	Design General information page					Lan	0	1	1	1	1	0	0	0	0	0
T2	0201	Design Subject instruction page					Ky	0	1	1	1	1	0	0	0	0	0
T2	0202	Update Design Subject instruction page					Ninh	0	1	1	1	1	0	0	0	0	0
T2	0203	Design Task list page					Quynh	0	1	1	1	1	0	0	0	0	0
T2	0204	Design Task detail page					Quynh	0	1	1	1	1	0	0	0	0	0
T7	0701	Design Signin page					Ninh	0	1	1	1	1	0	0	0	0	0
T8	0801	Design User profile page					Ninh	0	1	1	1	1	0	0	0	0	0
T9	0901	Design User profile edit page					Ninh	0	1	1	1	1	0	0	0	0	0
T6	0601	Design Activities log page					Lan	0	1	1	1	1	0	0	0	0	0
T11	1101	Design Activities log page (for all user)					Lan	0	1	1	1	1	0	0	0	0	0
T10	1001	Design User list page					Ninh	0	1	1	1	1	0	0	0	0	0
T0	0004	Design Home page					Lan	0	3	3	3	3	0	0	0	0	0
T0	0005	Review Design pages					Tuan	0	2	2	2	2	0	0	0	0	0
T0	0006	Make framework					Giang	0	2	2	2	2	0	0	0	0	0
T0	0007	Implement database model					Ky	0	2	2	2	2	0	0	0	0	0
T0	0008	Writing sample data for tests					Mui	0	2	2	2	2	0	0	0	0	0
T0	0010	Create static home pages					Giang	0	4	4	4	4	0	0	0	0	0
T7	0702	Make signin page					Giang	0	4	4	4	4	0	0	0	0	0
T3	0301	Create report view page					Lan	0	6	6	6	6	6	6	3	0	0
T3	0302	Create report update function					Mui	0	10	10	10	10	10	10	7	0	0
T10	1002	List all trainees					Quynh	0	2	2	2	2	0	0	0	0	0
T8	0802	Create public profile page of trainee					Mui	0	6	6	6	6	6	0	0	0	0
T4	0401	Create progress bar on trainee home page					Ninh	0	7	7	7	7	7	7	4	0	0
T2	0205	Create progress bar on subject page					Lan	0	7	7	7	7	7	7	3	0	0
T6	0602	Create trainee activity feed in trainee home page					Quynh	0	4	4	4	4	4	4	2	0	0
T6	0603	Create trainee activity feed of a subject on subject page					Quynh	0	10	10	10	10	10	10	5	0	0
T5	0501	Create Calendar page					0	0	0	0	0	0	0	0	0	0
T12	1201	Make start course function					Giang	0	10	10	10	10	10	0	0	0	0
T2	0208	Make finish subject function					Giang	0	7	7	7	7	7	7	0	0	0
T1	0102	Create course view page					Ky	0	7	7	7	7	7	0	0	0	0
T9	0902	Create edit profile page					Mui	0	2	2	2	2	2	0	0	0	0
T0	0011	Make home page, layout & css					Ninh	0	7	7	7	7	7	0	0	0	0
T0	0014	Apply css					Ninh	3	6	6	6	6	6	5	4	3	3
T11	1102	Create trainee activity feed of all training in course					7	7	7	7	7	7	7	7	7	7
T7	0703	Test signin page					Ky	1	1	1	1	1	1	1	1	1	1
T8	0803	Test profile page					Giang	1	1	1	1	1	1	1	1	1	1
T9	0903	Test edit profie					Giang	1	1	1	1	1	1	1	1	1	1
T1	0103	Test Course instruction page					1	1	1	1	1	1	1	1	1	1
T4	0402	Test Course progress bar					1	1	1	1	1	1	1	1	1	1
T2	0206	Test Subject instruction page					1	1	1	1	1	1	1	1	1	1
T2	0207	Test Subject progress bar					1	1	1	1	1	1	1	1	1	1
T12	1202	Test Start course function					3	3	3	3	3	3	3	3	3	3
T11	1103	Test Activity of course					2	2	2	2	2	2	2	2	2	2
T6	0604	Test my Activity in course					Giang	2	2	2	2	2	2	2	2	2	2
T6	0605	Test my Activity in subject					1	1	1	1	1	1	1	1	1	1
T3	0303	Test update report function					3	3	3	3	3	3	3	3	3	3
T10	1003	Test user list					1	1	1	1	1	1	1	1	1	1
T5	0502	Test calendar					4	4	4	4	4	4	4	4	4	4
T0	0012	Test home page					2	2	2	2	2	2	2	2	2	2

ISSUES:
	TuanCA
	NinhTMH
	LanDT
	Ky
	Mui
	Quynh
	Giang

## Sprint2
				Lost Hour	0					Holiday
				WH	35
				Hang	5
				Ninh	5
				Lan	5
				Ky	5
				Mui	5
				Quynh	5
				Giang	5
				Start Date	11/14/2013
				Date	14	15	16	17	18	19	20	21	22	23	24	25
				W	R	1	2	2	2	3	4	5	6	7	7	7	8	Saturday
				100%	0%	249	214	214	214	179	144	109	74	39	39	39	4	Sunday
StoryID	TaskID	Task					249	0	249	226	219	211	153	149	126	94	72	50	50	0
	2001	Make Sprint backlog					0	21	0	0	0	0	0	0	0	0	0	0	0
	2002	Make sample data					0	5	5	5	5	0	0	0	0	0	0	0	0
	2003	Design List all Trainees					0	2	2	2	2	0	0	0	0	0	0	0	0
	2004	Design View Profile					0	2	2	2	2	0	0	0	0	0	0	0	0
	2005	Design List all Courses					0	2	2	2	2	0	0	0	0	0	0	0	0
	2006	Design New course					0	4	4	4	4	0	0	0	0	0	0	0	0
	2007	Design View Course Detail					0	4	4	4	4	0	0	0	0	0	0	0	0
	2008	Design Edit course					0	2	2	2	2	0	0	0	0	0	0	0	0
	2009	Design Assign trainee to course					0	2	2	2	2	0	0	0	0	0	0	0	0
	2010	Design Home page					0	3	3	3	3	0	0	0	0	0	0	0	0
	2011	Apply CSS for all screens					0	20	18	18	18	16	12	8	5	2	0	0	0
	2012	Sign in / sign out					Giang	0	7	7	0	0	0	0	0	0	0	0	0	0
	2013	List all Trainees					Hang	0	5	5	5	5	0	0	0	0	0	0	0	0
	2014	View trainee profile					Ky	0	8	8	8	0	0	0	0	0	0	0	0	0
	2015	Assign trainee to course					Quynh	0	10	10	10	10	10	10	5	0	0	0	0	0
	2016	List all Courses					Lan	0	5	5	5	5	0	0	0	0	0	0	0	0
	2017	New course					Giang	0	10	10	10	10	10	10	5	2	0	0	0	0
	2018	Edit course					Giang	0	10	10	10	10	10	10	10	5	0	0	0	0
	2019	View course					Mui	0	10	10	10	10	0	0	0	0	0	0	0	0
	2020	Start course					Lan	0	5	5	5	5	5	5	5	0	0	0	0	0
	2021	Finish subject					Ky	0	8	8	8	8	8	8	4	1	0	0	0	0
	2022	Make Home page					Ninh	0	10	10	10	10	0	0	0	0	0	0	0	0
	2023	Write Sign in / sign out PCL					Hang	0	2	2	2	2	2	2	2	2	0	0	0	0
	2024	Write List all trainees PCL					Hang	0	2	2	2	2	2	2	0	0	0	0	0	0
	2025	Write Profile page PCL					Hang	0	3	3	3	3	3	3	3	0	0	0	0	0
	2026	Write Assign trainee to course PCL					Quynh	0	2	2	2	2	2	2	2	2	0	0	0	0
	2027	Write List all course PCL					Lan	0	2	2	2	2	2	2	2	0	0	0	0	0
	2028	Write New course PCL					Mui	0	3	3	3	3	3	3	3	0	0	0	0	0
	2029	Write Edit course PCL					Ky	0	3	3	3	3	3	3	3	3	0	0	0	0
	2030	Write View course PCL					Mui	0	3	3	3	3	3	3	0	0	0	0	0	0
	2031	Write Start course PCL					Mui	0	2	2	2	2	2	2	2	2	0	0	0	0
	2032	Write Finish subject PCL					Lan	0	2	2	2	2	2	2	2	2	0	0	0	0
	2033	Test Sign in / sign out					Hang	0	2	2	2	2	2	2	2	2	2	0	0	0
	2034	Test List all trainees					Hang	0	2	2	2	2	2	2	2	2	2	0	0	0
	2035	Test Profile page					Hang	0	2	2	2	2	2	2	2	2	2	0	0	0
	2036	Test Assign trainee to course					Quynh	0	2	2	2	2	2	2	2	2	2	0	0	0
	2037	Test List all course					Lan	0	2	2	2	2	2	2	2	2	2	0	0	0
	2038	Test New course					Mui	0	2	2	2	2	2	2	2	2	2	0	0	0
	2039	Test Edit course					Ky	0	2	2	2	2	2	2	2	2	2	0	0	0
	2040	Test View course					Mui	0	2	2	2	2	2	2	2	2	2	0	0	0
	2041	Test Start course					Mui	0	2	2	2	2	2	2	2	2	2	0	0	0
	2042	Test Finish subject					Lan	0	2	2	2	2	2	2	2	2	2	0	0	0
	2043	Fixbug Sign in / sign out					Giang	0	5	5	5	5	5	5	5	5	5	5	5	0
	2044	Fixbug List all trainees					Hang	0	5	5	5	5	5	5	5	5	5	5	5	0
	2045	Fixbug Trainee Profile page					Ky	0	5	5	5	5	5	5	5	5	5	5	5	0
	2046	Fixbug Assign trainee to course					Quynh	0	5	5	5	5	5	5	5	5	5	5	5	0
	2047	Fixbug List all course					Lan	0	5	5	5	5	5	5	5	5	5	5	5	0
	2048	Fixbug New course					Giang	0	5	5	5	5	5	5	5	5	5	5	5	0
	2049	Fixbug Edit course					Giang	0	5	5	5	5	5	5	5	5	5	5	5	0
	2050	Fixbug View course					Mui	0	5	5	5	5	5	5	5	5	5	5	5	0
	2051	Fixbug Start course					Lan	0	5	5	5	5	5	5	5	5	5	5	5	0
	2052	Fixbug Finish subject					Ky	0	5	5	5	5	5	5	5	5	5	5	5	0

ISSUES:
	Hang
	NinhTMH
	LanDT
	Ky
	Mui
	Quynh
	Giang

## ScrumIntro
Roles
	Product owner
		• defines product, releases, ROI, ...					• respects team estimates
		• represents customer and users for the team					• respects sprint planning
		• manages the Product Backlog
		• accepts work

	Team
		• typically 5-9 people					• respects Product Owner prio’s
		• cross-functional					• respects Scrum values and process
		• self-organizing and empowered

	Master
		• guards the Scrum process and the improvement cycle					• respects team decisions
		• removes impediments
		• motivates and coaches the team
		• facilitates collaboration

Artifacts
		• Product backlog
		• Sprint backlog
		• Burndown charts

Ceremonies
		• Estimation meeting
		• Planning meeting
		• Daily Scrum
		• Sprint review
		– demo
		– retrospective

Phases
	Planning
	Architecture / High level design
	Development		iteractive cycle

References:
	http://en.wikipedia.org/wiki/Scrum_(development)#Core_Scrum_roles
	http://www.xpday.net/html/Xpday2009/ScrumForDummies_handouts.pdf
	http://agileintro.wordpress.com/2008/01/10/all-about-scrum/

## 'file:///home/chuanhtuan/rails_projects/tms/document/TMS_Backlog_v1.0.xlsx'#Product Backlog
Sprint				Remaining

1				10
1				15
1				20
1				4
1				20
1				20

1				0
1				0
1				0

1				0
1				0
1				0