## Releases
Release	Sprint	Starting Date	Ending Date	Remaining	Description
1	1	1-Nov-13	9-Nov-13	0

## Pre-Game
Start Date	11/28/2011
			Working Day	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
#	Task		Remaining	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
1	Gather requirement
2	Define Architecture
3	Build Project framework

## Product Backlog
User		StoryID	Category	Story	Constraint	BR	Sprint	Priority	Estimated	Actual	Remaining		SD			0.20
Trainee				As a trainee
		T1	Course	View instructions about what the things I have to learn			1	1	4	0	9			4.8	0
		T2	Subject	View the instruction about a thing I have to learn			1	1	4	0	10			4.8	0
		T3	Subject	Report day by day			1	2	15	0	20			18	0
		T4	Course	View my current progress			1	1	4	0	8			4.8	0
		T5	Calendar	View my training calendar			1	3	20	0	24			24	0
		T6	Activity	View all histories of my activity in course, in subject			1	2	7
		T7	User	Can signin			1	1	2
		T8	User	View my profile, member profile			1	2	4
		T9	User	Edit my profile			1	2	2
		T10	User	View members of course			1	1	1
		T11	Activity	View all activity histories of course			1	2	4
		T12	Course	Can start course			1	2	7
														0	0
Suppervisor				As a suppervisor										0	0
		S1					1	1	0	0	0			0	0
		S2					1	1	0	0	0			0	0
		S3					1	1	0	0	0			0	0
														0	0
Operator				As CG's Operator										0	0
		O1					1	1	0	0	0			0	0
		O2					1	1	0	0	0			0	0
		O3					1	1	0	0	0			0	0
														0	0

## Business Rules
ID	Description	Related Rules	References	Note
BR1
BR2
BR3
BR4
BR5
BR6
BR7
BR8
BR9
BR10
BR11
BR15

	Constraint
	Computation
	Action/Switch action/Execute action	Enable/Disable/Execute a process
	Data Action	A data action rule creates, modifies or deletes data
	Presentation Action

	ID
	Description	Example	Workflow	Workflow
	Related Rules
	References
	Assumptions
	Notes	Concerns

## Sprint1
				Lost Hour	0					Holiday
				WH	42
				Tuan	0
				Ninh	7
				Lan	7
				Ky	7
				Mui	7
				Quynh	7
				Giang	7
				Start Date	11/1/2013
				Date	01	02	03	04	05	06	07	08	09
				W	R	1	1	1	2	3	4	5	6	6	Saturday
				24%	76%	210	210	210	168	126	84	42	0	0	Sunday
StoryID	TaskID	Task					51	159	210	210	210	192	159	159	159	159	159
T0	001	Make sprint backlog					6	42	42	42	24	6	6	6	6	6
T0	002	Design database model					Mui	0	4	4	4	4	0	0	0	0	0
T0	003	Review DB					0	2	2	2	2	0	0	0	0	0
T1	101	Design General information page					Lan	1	1	1	1	1	1	1	1	1	1
T2	201	Design Subject instruction page					Ky	0	1	1	1	1	0	0	0	0	0
T2	202	Update Design Subject instruction page					Ninh	1	1	1	1	1	1	1	1	1	1
T2	203	Design Task list page					Quynh	0	1	1	1	1	0	0	0	0	0
T2	204	Design Task detail page					Quynh	0	1	1	1	1	0	0	0	0	0
T7	701	Design Signin page					Ninh	0	1	1	1	1	0	0	0	0	0
T8	801	Design User profile page					Ninh	0	1	1	1	1	0	0	0	0	0
T9	901	Design User profile edit page					Ninh	0	1	1	1	1	0	0	0	0	0
T6	601	Design Activities log page					Lan	1	1	1	1	1	1	1	1	1	1
T11	1101	Design Activities log page (for all user)					Lan	1	1	1	1	1	1	1	1	1	1
T10	1001	Design User list page					Ninh	1	1	1	1	1	1	1	1	1	1
T0	004	Design Home page					Lan	3	3	3	3	3	3	3	3	3	3
T0	005	Review Design pages					1	2	2	2	2	1	1	1	1	1
T0	006	Make framework					Giang	0	2	2	2	2	0	0	0	0	0
T0	007	Implement database model					Ky	2	2	2	2	2	2	2	2	2	2
T0	008	Writing sample data for tests					Mui	2	2	2	2	2	2	2	2	2	2
T0	010	Create static home pages					Giang	4	4	4	4	4	4	4	4	4	4
T7	702	Make signin page					Giang	4	4	4	4	4	4	4	4	4	4
T3	301	Create report view page					6	6	6	6	6	6	6	6	6	6
T3	302	Create report update function					10	10	10	10	10	10	10	10	10	10
T10	1002	List all trainees					Quynh	2	2	2	2	2	2	2	2	2	2
T8	802	Create public profile page of trainee					6	6	6	6	6	6	6	6	6	6
T4	401	Create progress bar on trainee home page					7	7	7	7	7	7	7	7	7	7
T2	205	Create progress bar on subject page					7	7	7	7	7	7	7	7	7	7
T6	602	Create trainee activity feed in trainee home page					4	4	4	4	4	4	4	4	4	4
T6	603	Create trainee activity feed of a subject on subject page					10	10	10	10	10	10	10	10	10	10
T5	501	Create Calendar page					20	20	20	20	20	20	20	20	20	20
T12	1201	Make start course function					10	10	10	10	10	10	10	10	10	10
T1	102	Create course view page					7	7	7	7	7	7	7	7	7	7
T9	902	Create edit profile page					2	2	2	2	2	2	2	2	2	2
T0	011	Make home page					7	7	7	7	7	7	7	7	7	7
T11	1102	Create trainee activity feed of all training in course					7	7	7	7	7	7	7	7	7	7
T7	703	Test signin page					1	1	1	1	1	1	1	1	1	1
T8	803	Test profile page					1	1	1	1	1	1	1	1	1	1
T9	903	Test edit profie					1	1	1	1	1	1	1	1	1	1
T1	103	Test Course instruction page					1	1	1	1	1	1	1	1	1	1
T4	402	Test Course progress bar					1	1	1	1	1	1	1	1	1	1
T2	206	Test Subject instruction page					1	1	1	1	1	1	1	1	1	1
T2	207	Test Subject progress bar					1	1	1	1	1	1	1	1	1	1
T12	1202	Test Start course function					4	4	4	4	4	4	4	4	4	4
T11	1103	Test Activity of course					2	2	2	2	2	2	2	2	2	2
T6	604	Test my Activity in course					2	2	2	2	2	2	2	2	2	2
T6	605	Test my Activity in subject					1	1	1	1	1	1	1	1	1	1
T3	303	Test update report function					4	4	4	4	4	4	4	4	4	4
T10	1003	Test user list					1	1	1	1	1	1	1	1	1	1
T5	502	Test calendar					4	4	4	4	4	4	4	4	4	4
T0	012	Test home page					2	2	2	2	2	2	2	2	2	2

ISSUES:
	TuanCA
	NinhTMH
	LanDT
	Ky
	Mui
	Quynh
	Giang

## ScrumIntro
Roles
	Product owner
		• defines product, releases, ROI, ...					• respects team estimates
		• represents customer and users for the team					• respects sprint planning
		• manages the Product Backlog
		• accepts work

	Team
		• typically 5-9 people					• respects Product Owner prio’s
		• cross-functional					• respects Scrum values and process
		• self-organizing and empowered

	Master
		• guards the Scrum process and the improvement cycle					• respects team decisions
		• removes impediments
		• motivates and coaches the team
		• facilitates collaboration

Artifacts
		• Product backlog
		• Sprint backlog
		• Burndown charts

Ceremonies
		• Estimation meeting
		• Planning meeting
		• Daily Scrum
		• Sprint review
		– demo
		– retrospective

Phases
	Planning
	Architecture / High level design
	Development		iteractive cycle

References:
	http://en.wikipedia.org/wiki/Scrum_(development)#Core_Scrum_roles
	http://www.xpday.net/html/Xpday2009/ScrumForDummies_handouts.pdf
	http://agileintro.wordpress.com/2008/01/10/all-about-scrum/

## 'file:///home/chuanhtuan/rails_projects/tms/document/TMS_Backlog_v1.0.xlsx'#Product Backlog
Sprint				Remaining

1				10
1				15
1				20
1				4
1				20
1				20

1				0
1				0
1				0

1				0
1				0
1				0